## Timeline
Project Name |  | Total Duration(Days) | Start Date | End Date | Submission date
Agriculture Management System |  | 30 | 20/08/2021 | 25/09/2021 | 29/09/2021
Sl No. | Task Descriptions | Start Date | End Date | Duration
1 | Planning/Design
1.1 | Project Defination | 20/08/2021 | 22/08/2021 | 3
1.2 | Finish webpage | 23/08/2021 | 25/08/2021 | 2
1.3 | Project Design | 26/08/2021 | 29/08/2021 | 3
2 | Coding
2.1 | Phase 1 | 30/08/2021 | 2021-03-09 | 5
2.2 | Phase 2 | 2021-04-09 | 2021-07-09 | 4
2.3 | Additional Features | 2021-07-09 | 2021-08-09 | 2
3 | Testing
3.1 | Phase 1 Testing | 17/09/2021 | 19/09/2021 | 3
3.2 | Modification /Any changes | 20/09/2021 | 20/9/2021 | 1
3.3 | Phase 2 Testing | 21/9/2021 | 21/9/2021 | 1
3.4 | Modification /Any changes | 22/9/2021 | 22/9/2021 | 1
3.5 | Final Testing | 23/09/2021 | 23/09/2021 | 1
4 | Documentation
4.1 | User Guide | 24/9/2021 | 24/9/2021 | 1
4.2 | Presentation | 25/9/2021 | 25/9/2021 | 1

## Roles & Responsiblity
Roles And Responsiblities
1 | Role | Team Lead
| Member Name | Anuradha Shivaji Sangale
| PRN No | 210543181009
| Description | BackEnd Coding
2 | Role | Team Member
| Member Name | Varsha Bhaskar Pawar
| PRN No | 210543181069
| Description | FrontEnd Coding
3 | Role | Team Member
| Member Name | Vilas Nagoji Oulkar
| PRN No | 210543181057
| Description | BackEnd Coding
4 | Role | Team Member
| Member Name | Akash Shivkumar Bhosale
| PRN No | 210543181014
| Description | FrontEnd Coding